## Feedback Tracker
Samavesh × Dhwani RIS — Wireframe Feedback Tracker (Phase 1)
Please log feedback screen-by-screen below. ¦ Target: by Wed 17-Jun-2026
ID | Profile | Section / Screen | Element / Field | Feedback / Change Requested | Type | Dhwani's Response | Status
1 | General | Login & Authentication | Student Login | Incorporate an email OTP verification when we onboard any student. | New Requirement
2 | General | Navigation / Layout / General | Student/ Fellow/ Admin/ Mentor | Can we hide these options and only have login ID and password visibile. Now based on everyones individual login ID and password, respective individuals would be able to login as per their role | UI / Design
3 | Student | Home Screen | WhatsApp reach out button | Include an integrated whatsapp chat button that will redirect a student to WhatsApp and directly send their queries | Enhancement
| Student | Home Screen | UI | 3 tabs: Scholarships identified, documents accepted, and expected amount can be moved up the order, above 'My scholarship applications' section | UI / Design
4 | Student | Scholarship Tab |  | 1. Also eligible scholarships section can be removed 2. Ready to submit section can also be removed 3. Instead we can only have 'My Active Scholarships' section and list out all the scholarships that a student is eligible for with their status/stage | UI / Design
5 | Student | Documents Tab | Sub-document attachment | Behind every main document (caste, income, domicile, etc) which is missing, there should be a drop down to add sub documents (attachment) by the student, which a fellow can view and download. This should be enabled only if the student marks 'don't have' in the student onboarding form | Enhancement
6 | Student | Profile
7 | Fellow | Home Dashboard |  | Fellows home dashboard should have a login and a log out button to capture their attendance. | New Requirement
8 | Fellow | My Students |  | My students' and 'my cases' pages can be merged and made into one single page as 'my student case' page. All the features that are unique on both the pages can be brought on one single page, like for example, search bar to search students by their names, onboarded on feature, list of to do tasks, in-progress, on hold, all such features can be brought on one single page by merging the two. | Enhancement
9 | Fellow | My Cases
10 | Fellow | Onboarding Form |  | Can we have a stduent onboarding form link that can be sent out to students for them to fill out independantly. | Enhancement
11 | Fellow | Scholarship Data Entry Form |  | As per our last conversation, The scholarship data entry form should be enabled on the students profile (fellow view), once the student is onboarded on our system. This form should reflect on the student view | Enhancement
12 | Fellow | Student Profile View |  | Student profile section to have notes section to capture notes. This will be filled by the fellows which should also reflect inperson or virtual meeting/ date and time | New Requirement
13 | Admin | MIS Dashboard
14 | Admin | Cases & Tasks (Reassignment)
15 | Admin | Scholarship Catalog
16 | Admin | Manage Students
17 | Admin | Fellow & Users
18 | Admin | Document Verification
19
20
21
22
23
24
25
26
27
28
29
30